## Slide 1: Roma Inclusion & Empowerment
Vassiliki Staikou
Ministry of Labour & Social Security

## Slide 2: Recent Milestones
By the end of Jan 2023 the PO had announced 2 remaining Calls, 2 SGS related ones. Namely:
On July 13th 2022 a Call regarding SGS 1 was issued having incorporated IPO’ s consultancy and focus group methodology results resulting in the submission of 13 Applications On 30th April 2023 five SGS 1 Project Contracts were signed, enabling the implementation of 5 Roma Empowerment Projects targeting Roma Youth and Women
On 20th January 2023 a Call regarding SGS 2 was issued having incorporated IPO’ s and
FMO’s consultancy and remarks On 9th June one 2023 SGS 2 Project Contract was
signed launching the participation of Roma school children in summer camps
By now the PO has activated all foreseen ‘management cost’ contracts, 2 PDP and 2 SGS related ones. Relevant figures:
Calls : 99,3%
Project Contracts: 99,3%
Expenditure: 39,6% (PDP 1) 31,33 (Management Cost)

## Slide 3: PDP 1- Operation of Task Force Units in 4 Territories Champion actions: -drafting territorial Roma inclusion Strategies -offering structured help to Roma people so as to become visible -monitoring of school attendance and academic progress in 4 Territories -studying the possibility of applying relocation schemes in 4 Territories -strong partnership with the Roma Community Centres & Local Authorities -Policy proposals Measurable achievements: -90 meetings with pertinent Public Authorities -100 Employment Counselors trained by the Task Force -20 Task Force Experts & Roma mediators trained 75 visits to Roma Communities
APRIL 2021
Call for Task Force Unit Recruitment
Dec 2021
25 Contracts signed
JANUARY 2021 Contract between OP & PP
MAY 21- JAN 22 Procurement of equipped offices, cars, cell phones, internet connections etc
JUNE 2022
Task Force Training Seminars
DEC 21-today
Task Force Unit in operation

## Slide 4: Task Force in Action
Training school teachers
Networking with a Roma NGO
Visiting a Roma settlement
Informing Roma people about cancer prevention examinations
Networking with a Roma Community Centre
Task Force in Action

## Slide 5: PDP 2- soft actions addressed to Roma children, women and unemployed youth in Pelekas-Katerini
DECEMBER 2022-JANUARY 2023
The Municipality of Katerini informed the PO officially of the cancellation of the housing scheme due to PUBLIC HEALTH reasons, since the existing legislation does not provide for the location and construction of a settlement in a restored HADA (registered area of uncontrolled waste disposal)
Soft Actions are being implemented successfully in Katerini-Pelekas;
-Educational support activities, such as a study centre, tutoring in Maths, Physics, , Greek Language, school transport,
-Cultural, sport and recreational activities to facilitate dialogue between Roma and non-Roma communities, such as the creation of a football & a swimming team

## Slide 6: SGS 1- Roma Women and Youth Empowerment 5 Projects are being implemented successfully • All 4 call territories are covered by the actions foreseen by the PPs; • There are a large variety of types of PPs implementing SGS 1 projects ; universities, research institutes, vocational training centers and consulting agencies, local government agencies and professional unions, as well as NGOs & specifically Roma NGOs; • Two of three foreseen sets of Call actions Information-Awareness Raising-Combating Stereotypes & Vocational and Business Counselling – and their corresponding objectively verifiable indicators are fully covered by the candidates’ projects.
JULY 2022
Open Call for Proposals
OCT 2022
Deadline for Submission
NOV 2022-MAR 2023
Appraisal of 13 proposals completed
APR 2023
Project Contracts &
Implementation of Projects

## Slide 7: SGS 2- Promotion and Support of Roma children in summer camps
NOV 2022
Open Call for Proposals to be announced
JAN 2023
Deadline for Submission
MAR 2023
Appraisal Completed
JUN –AYG 2023
Project Contracts
Implementation of Projects

## Slide 8: Next Steps
A documenatry presenting the Task Force mandate and results to be produced- Dec 2023-April 2024
Bilateral Activities get started –Jan 2024
Next CC Meeting to take place in Spring 2024 jointly with the 2nd Communication Programme Event
Expenditure delays to mitigate–Dec 2023-April 2024

## Slide 9: Thank you very much! https://eeagrants-roma.gr/ Ε-Mail: info@eeagrants-roma.gr espa_apko@mou.gr